## Main-Task
Logistic Mangement System
Sr.No | Task | Features
1 | Defination | CRUD API and Consume React.js
2 | Timing or Planning for feartures | This week upadting and export data
3 | Extra or Add On | Pagination, Soft Delete, All Delete and Export
4 | Regular Task | API Validation
5 | Add on Learning | Linq Methods and Query

## Shedule-task
Logistic Management System
Sr. | Points/Task | Start Date | Deadline | Features Description | Priority | Task Status
1 | Database Design | 2025-06-10 | 2025-06-15 | Setup backend DB schema for logistics and .NET Web API | Medium | Completed
2 | All Tables Created in SQL | 2025-06-11 | 2025-06-16 | Implement schema for User, Shipment, Vehicle, Inventory | High | Completed
3 | User Authentication API | 2025-06-18 | 2025-06-25 | Login, Register, JWT Token | High | Completed
4 | Create and Consume Get APIs for All Tables | 2025-07-05 | 2025-07-13 | Develop basic GET APIs for Admin, Manager, Driver roles | Medium | Completed
5 | Implement All Table Search in React | 2025-07-17 | 2025-07-20 | Add search functionality in UI for orders and users | Medium | Completed
6 | Add Pagination to Customer Table in React | 2025-08-10 | 2025-08-18 | Paginate customer list on frontend | Hard | Completed
7 | Implement Soft and Hard Delete for Customers | 2025-08-12 | 2025-08-20 | Add logic to soft-delete & permanently delete customers (Add advanced) | Medium | Completed
8 | Update Operation for All Tables | 2025-08-14 | 2025-08-22 | Enable update functionality for all major entities | Medium | Completed
9 | Insert Operation for All Tables | 2025-08-15 | 2025-08-23 | Enable add/create functionality for all major entities | Medium | Completed
10 | Implement DeleteAll Tables | 2025-08-17 | 2025-08-25 | Add advanced or repeat deleteall logic | Low | Completed
11 | Implement One Table Export Data | 2025-08-17 | 2025-08-25 | Add advanced Export PDF in React.jsx | Low | Completed